## Close-Out report
SUB-GRANT THEME | IMPLEMENTATION OF STANDARDIZED BIOINFORMATICS PRACTICES, PIPELINES, AND DATA STRUCTURES IN SARS-COV-2 OR AMR
SUB-GRANTEE: | INSTITUT NATIONAL DE RECHERCHE BIOMEDICALE
REPORT TYPE: | CLOSE-OUT REPORT
DUE DATE: | 2022-10-31
PERIOD: | <<INSERT DATES COVERED BY THE CLOSE-OUT REPORT>>
REPORT COMPILED BY: | PLACIDE MBALA KINGEBENI
SIGNED | <<SIGNATURE OF INSTITUTION'S AUTHORIZED SIGNATORY>>
DATE OF SUBMISSION: | 2022-11-02
1. INTRODUCTION:
Brief one to two paragraph introduction (summarize key points of the report of the full project).
The Implementation of standardized bioinformatics practices, pipelines, and data structures in SARS-CoV-2 sequencing laboratories in LMICs is the sub-grant theme which fund is managed by the INRB laboratory to improve some of the aspects related to the capacity building of the bioinformatic team and the reinforcement of the dry lab infrastructure. This work is about the Quality control of the generated sequences making sure those match the PHA4GE QC acceptance criteria; the hardware devices to supply the bioinformatic laboratory to run pipelines and softwares; the SOP done to share how fastq, fasta are generated and how sequences are submitted to Gisaid; Gathering contextual data about the selected sequences and writing a detailed report of all activities.
2. PROGRESS AGAINST PLANNED ACTIVITIES OR DELIVERABLES:
Provide a brief narrative summary ( 1-5 lines) of progress made on completion of planned activities or deliverables. Where challenges were met, please describe how you managed to resolve the challenges or proposed ideas on how to resolve the challenges.
SARS CoV-2 THEME
Deliverable 1: Generate SARS-CoV-2 viral sequence data on at least two small batches of samples (approximately 12 samples each) 24 samples have been selected from 6 SARS-CoV-2 batches , all batches were run on a Nanopore platform using the Midnight protocol . At the end, 24 SARS-CoV-2 viral have been generated for further analysis
Deliverable 2: Submit sequence and contextual data to INSDC repositories (e.g. SRA+GenBank (NCBI) or ENA (EMBL-EBI)) and GISAID A SOP has been written to capture the steps for a single and a batch submission. SOP : https://inrb-labgenpath-pha4ge.gitbook.io/submission-of-sequences-on-gisaid/. In total 24 sequences have been submitted to Gisaid. Hopefully , the laboratory is planning to submit to genbank thanks to the NCBI sample submission provided by PHA4GE.
Deliverable 3: Document implemented bioinformatics protocols (i.e. on protocols.io or GitHub using a GitBook (https://www.gitbook.com/) Midnight Protocol has been used to describe different steps to get the Fastqs and the pipeline articwrapper that encompasses all the single commands in the https://artic.network/ncov-2019/ncov2019-bioinformatics-sop.html into one command line. SOP : https://inrb-pha4ge.gitbook.io/fastq-and-fasta-generation-processes/
Deliverable 4: Write a report outlining successes and challenges, and suggestions for other labs implementing PHA4GE recommendations and resources for SARS-CoV-2 analyses The SARS-CoV-2 recombination finder approch, the nextclade quality control , the Quality control criteria and some other tools like ncov-qc and fastqc are differents area of analysis that the bioinformatic team did focus on. Fastqs and fasta files have been regenerated and from those, downstream analysis suggested by the PHA4GE bioinformatic pipelines and visualisation team have been conducted. Setting up the pipelines was successfully done for many of the suggested pipelines. The team only have difficulty to interpret some outputs from those pipelines. We may suggest to have a kind of training to have a good hands on those pipelines. Having some data as example in the pipeline repository will while installing to understand better how things work.
3. FINANCIAL STATUS AND PERFORMANCE
Provide a review of the full project’s financial status. All amounts are to be entered in USD.
Total Amount of Grant |  |  |  | 30000
SUMMARY
2.1 Total value of grant (as per grant agreement) |  |  |  | 30000
2.2 Total amount spent during period |  |  |  | 23463.22
2.3 Balance (Surplus or Deficit) |  |  |  | 6519.73
EXPENDITURE REPORT
Provide a breakdown of expenditure e.g. salaries, equipment, infrastructure etc. against the approved budget items.
NB: Please insert additional rows if there are additional Budget Line Items you need to report on.
Budget Line Item | Amount Approved as per the Budget | Amount spent on this Item | Amount remaining ( if applicable) | Comments
labour | 11795.19 | 11795.19 |  | 4 people committed to the activity
Trainings and capacity building | 4910 | 2566
Office supplies | 450
Laptop and SSD | 5500 | 9102.03
Geneious software licence | 800
Wifi | 600
Publication costs | 2500
Shipping | 2000
Indirect costs | 1427.76
Total | 29982.95 | 23463.22 | 6519.73
4. LESSONS LEARNT
Provide a few lessons learnt throughout the full project:
A standardized spreadsheet for data collection is powerful for fair data analysis
Specific validated Quality control tools are efficient
To Combine and compare analyzed results from different QC tools is important to evaluate the accuracy and powerfulness of QC pipelines
To set a batch of QC analysis in a laboratory before any sequence sharing is crucial for further analysis
To bioinformatic infrastructure needs high quality devices for fast and best results
It is so necessary for the laboratory to keep on skilling up its staff members
NB. By signing this report you are confirming that the information contained in the progress and financial report is accurate and true and can be independently verified. If need be, PHA4GE may request further details regarding this report.